## MOM
Minutes of Meeting
Doc ID : |  | Trantor/MOM/Ver 1.1 |  |  | Date Released : 28/1/2016
Participants |  | Offsite team and Onsite team
Purpose |  | Fry's Web-Team– To address the blockers,issues and release plan
Venue |  | Teleconf
Prepared by |  | Amit Kapoor, Preeti Khanna
To |  | Dhruv
Attendance |  | WebTeam1 and WebTeam2
Absence
S.no. |  | Points Discussed
1 |  | SCR#504204, 515233 :- Discussed that code has been deployed in production environment on 26th Jan. No performance issues reported after migrating to new MySql server.
2 |  | SCR#558221:- Login page is deployed on jback301. We are releasing responsive 'Your Cart' page on 28th Jan for QA.
3 |  | SCR#534514:- Dhruv to confirm about 'Password Reset' functionality.
4 |  | SCR#521130:- Home delivery :- Discussed about slotNB. No. of slots required for a particular truck will depend upon zone. If value of truckId =-1 then that row corresponding to zone tells us abou the number of slots required. Credit card functionality was discussed. Need to provide the required table structure in FSSDB.
5 |  | For Invoice and catalog OTProcess we need to do code changes for keeping deifferent pervasive properties in officetool. Properties
6 |  | 1) Discussed about sweepstakes table structure. Now in frys_sweepstakes_enteries we will keep three columns ID, email, CreateDate. Rest of the information will be captured in JI_account_member_1 of mysql. 2) In signup URL, contest parameter will have contest Name as its value not ID.3) Both day_phone and evening_phone columns in J1_address_1 table will save same contact number, captured from signUP page.4) ZipCode to be updated for both billing and shipping in J1_address_1.
7 |  | Ticket#571743 : Discussed about restriction of shipping option for freight cart. Freight cart will not show ground/ultasaver even if there is product with compat_95_flag =9
8 |  | 540387 and 549768 Dhruv will let us know about these.
S.no | Item |  | By When - DD/MM/YYYY | By Whom : Responsibility
1 | SCR#558221:- Cart page |  | 28/01/2016 | Team1 to release code for QA
2 | SCR521130:- Home delivery credit card logic |  | 28/01/2016 | Team 1 to provide the required structure for the table in FSSDB
3 | SCR#504204: Mysql Release |  | 28/01/2016 | Team 1 to explore production logs for any exceptions.
Note: | 1. The MOM should be tracked and maintained on Weekly Basis based on client interactions in different sheets in one file. 2. The sheet should be named as date of meeting/MOM release date.